# 3.5 Major Technical Challenges and Possible Solutions

| Challenge | Why it is hard for our team | Possible solution or approach | Decision point |
| --- | --- | --- | --- |
| Wheel and suspension strength | Our printed rims and tyres face impacts and side loads. | We will load-test one wheel assembly on gaps and rocks before printing all four. | 14 Nov 2026 Drawing release |
| Low mass with enough stiffness | Our estimate exceeds the 20 lb scoring target. | We will weigh assemblies and remove material only where strength tests allow. | 30 Jan 2027 Integration |
| Drive torque and speed | Motor torque, ESC ratings and full-charge speed need confirmation. | We will check loaded turning, current and stopping, then verify the speed limiter. | 30 Jan 2027 Rover tests |
| Live commands and radio reception | We must decode new commands while other hardware runs. | We will test unfamiliar APRS sequences with motors running and adjust antenna routing. | 30 Jan 2027 Integration |
| Accurate target ranging | Our camera and LiDAR may aim at different surfaces. | We will calibrate aiming and distance, retry failed readings, and flag unresolved results. | 30 Jan 2027 Calibration |
| Stable task power | Servo peaks and USB loads may cause Pi restarts. | We will check voltages with all loads running and test battery reserve through results review. | 30 Jan 2027 Integration |
| Imported component availability | Late parts could delay our planned 6 Nov bench checks. | We will confirm stock before ordering and check compatible alternatives if delivery slips. | 16 Oct 2026 Place orders |